## Artisan Connect
[5 empty] | Project Start Date: | 2022-02-20
Frontend | [6 empty] | Backend
Milestone 1 | Authentication | [5 empty] | Milestone 1 | Authentication |  |  |  | LEGEND
Tasks | Timeline |  | Comment | Status |  |  | Tasks | Timeline |  | Comment | Satus |  | Pending
| Start Date | End Date | [5 empty] | Start Date | End Date |  |  |  | Completed
Login Form | [6 empty] | Boostrapping | [5 empty] | In-Progress
Signup Form | [6 empty] | Model Design/Creation | [5 empty] | Cancel
Forget Password Form | [6 empty] | Unit Testing |  |  | Integration test pending
Login Form Input Validation | [6 empty] | Input Validation (Fluent Validator)
Signup Form Input Validation | [6 empty] | JWT Auth
Reset Form Input Validation | [6 empty] | Access Token Generation
Login Form Responsive Design | [6 empty] | Refresh Token Generation
Signup Form Responsive Design | [6 empty] | Token Validation
Reset Form Responsive Design | [6 empty] | Token Encryption
Stay login | [6 empty] | Email Varification
Token storage | [6 empty] | Password Varification
API Integration | [6 empty] | API Design |  |  | Awaiting QA
1. Register API | [6 empty] | API Development:
2. Login API | [6 empty] | 1. Login API
3. Refreshv Token API | [6 empty] | 2. Signup API
4. Forget Password API | [6 empty] | 3. Verify Email API
4. Refresh Token API
Milestone 2 | User Profile | [5 empty] | 5. Validate Refresh Token API
6. Revoke Token API
Code Refactor | [6 empty] | 7. Forget Password API
Responsive Design with Bootstrap 5 | [6 empty] | 8. Logout API
Global Config | [6 empty] | 9. Keep Me Login
1. Color Config | [6 empty] | 9. Hosting |  |  | Hosting account cannot be accessed
2. Font Family Config
Design Forbidden Page | [6 empty] | Milestone 2 | User Profile & Authorization
Design Error 404 Page | [6 empty] | Caching System |  |  | Improve data fetch performance
Design Email Confirmation Page | [6 empty] | Model Design/Creation | 2022-03-14 | 2022-03-16 | Customer, Artisan, Services, Categories, Adhoc
Design User Profile Page | [6 empty] | Unit Testing
1. Edit Profile | [6 empty] | Data Validation (Fluent Validator) | 2022-03-19 | 2022-03-19
2. Change Password | [6 empty] | Account Suspension
3. Upload Profile Picture | [6 empty] | Account Deletion
4. Delete Account | [6 empty] | Configure Azure File storage |  |  | Pending when we have Azure active account
5. Can View Service Histories |  |  | Ability to toggle pending and completed services |  |  |  | Profile Picture Upload |  |  | Pending when we have Azure active account
Design Artisan Profile Page | [6 empty] | CRUD Operations
1. Edit Profile | [6 empty] | 1. Create User Account | 2022-03-21 | 2022-03-22
2. Change Password | [6 empty] | 2. Read User Account
3. Upload Profile Picture | [6 empty] | 3. Update User Account
4. Delete Account | [6 empty] | 4. Delete User Account
5. Can View Service Histories |  |  | Ability to toggle pending and completed services |  |  |  | 5. Create Artisan Account | 2022-03-24 | 2022-03-25
6. Can Accept Service | [6 empty] | 6. Read Artisan Account
7. Can Decline Service | [6 empty] | 7. Update Artisan Account
Design Admin Page | [6 empty] | 8. Delete Artisan Account
1. Can View All Users Profiles | [6 empty] | 9. Suspend Artisan Account | 2022-03-26 | 2022-03-28
2. Can View All Artisans Accounts | [6 empty] | 10. Seed Admin Account
3. Can Create Artisan | [6 empty] | Role & Permission Management
4. Can Delete Artisan | [6 empty] | 1. Setup User Role | 2022-04-01 | 2022-04-04
5. Can Suspend Artisan | [6 empty] | 2. Setup Artisan Role
Authentication Token | [6 empty] | 3. Setup Admin Role
1. Store token in memeory | [6 empty] | Authorization |  |  | Route guard secured resources
2. Authomatic token refresh based on expiration | [6 empty] | 1. Role-based Authorization | 2022-04-06 | 2022-04-09
Onboading Pages | [6 empty] | 2. Policy-based Authorization
1. Regular User | [6 empty] | Authorization Middleware
2. Artisan | [6 empty] | 1. Resource Authorization
API Integration | [6 empty] | 2. Route Authorization
1. Create User API | [6 empty] | API Design
2. Query User API | [6 empty] | API Development:
3. Update User API | [6 empty] | 1. Create User API Endpoint | 2022-04-13 | 2022-04-16
4. Delete User API | [6 empty] | 2. Query User API Endpoint
5. Create Artisan API | [6 empty] | 3. Update User API Endpoint
6. Read Artisan API | [6 empty] | 4. Delete User API Endpoint
7. Update Artisan API | [6 empty] | 5. Create Artisan API Endpoint
8. Delete Artisan API | [6 empty] | 6. Read Artisan API Endpoint
9. Suspend Artisan API | [6 empty] | 7. Update Artisan API Endpoint
10. Upload Profile Photo API | [6 empty] | 8. Delete Artisan API Endpoint
11. Delete Profile Photo API | [6 empty] | 9. Suspend Artisan API Endpoint
10. Upload Profile Photo API | [6 empty] | 10. Upload Profile Photo API Endpoint |  |  | Pending when we have Azure active account
11. Delete Profile Photo API | [6 empty] | 11. Delete Profile Photo API Endpoint |  |  | Pending when we have Azure active account
Milestone 3 | Service Category | [5 empty] | Milestone 3 | Service Category
Design Services Page by Category |  |  | Add search box & Pagination |  |  |  | App Search
Design Service Providers (Artisans) Page by Category - (Name, Photo, Location, Rating) |  |  | Add search box & Pagination |  |  |  | 1. Global search | 2022-04-20 | 2022-04-22
Artisan Profile Page - As seen by the user |  |  | This page is seen by the user |  |  |  | 2. Content Specific Search
Design Service Booking Form |  |  | See requirement doc for details |  |  |  | Pagination
[7 empty] | Uploads |  |  | Pending when we have Azure active account
Milestone 4 | Reporting | [5 empty] | 1. Documents |  |  | Pending when we have Azure active account
[7 empty] | 2. Videos |  |  | Pending when we have Azure active account
Export the Different Tables to Excel/PDF |  |  | Add export functionality |  |  |  | 3. Images |  |  | Pending when we have Azure active account
[7 empty] | Accept Service | 2022-04-25 | 2022-04-27
Decline Service
Email Server Configuration
Email Notification for Rating
Email Templates
Admin Role
[7 empty] | 1. Create Service Category | 2022-04-28 | 2022-04-30
2. Create Services
3. Add Services to Categories
4. Update Service Category
5. Update Services
4. Delete Service Category
5. Delete Services
API Design
API Development
[7 empty] | 1. Create Service Category API Endpoint | 2022-05-03 | 2022-05-05
2. Create Services API Endpoint
3. Add Services to Categories API Endpoint
4. Update Service Category API Endpoint
5. Update Services API Endpoint
4. Delete Service Category API Endpoint
5. Delete Services API Endpoint
[7 empty] | 6. Query All Service API Endpoint | 2022-05-06 | 2022-05-10
7. Query All Categories API Endpoint
8. Query Services By Category API Endpoint
9. Query Services By User API Endpoint
10. Query Services By Artisan API Endpoint
[7 empty] | Milestone 4 | Database Design
[7 empty] | ER Definition | 2022-05-12 | 2022-05-14
ER Design
Database Configuration
Model Configuration
Model Mapping
[7 empty] | Schema Creation | 2022-05-18 | 2022-05-20
Database Migration
Deployment for Beta testing

## Facility Management
|  |  |  | Project Started on | 2022-02-16
Frontend | [5 empty] | Backend
Module 1 | Authentication |  |  |  |  | Module 1 | Authentication
| Start Date | End Date | Comment | Status |  |  | Start Date | End Date | Comment | Status
scaffolding | [5 empty] | Architecture
Login Screen | [5 empty] | Infrastucture
Register Screen | [5 empty] | Model Design
Forget password | [5 empty] | Application Logic
Secret storage
Module 2 | Administration |  |  |  |  | Module 2 | Administration
House Screen | [5 empty] | House domain models
Create House | [5 empty] | Resident models
Delete House | [5 empty] | Business logic
Add Resident | [5 empty] | Data validation
Remove Resident | [5 empty] | Data import and export
Visitor Logs | [5 empty] | Database design (ERD)
Email Broadcast | [5 empty] | Database Schema
Database Syncronization
API Design & Development
Email implemenation
Module 3 | Maintenance and Service Charge |  |  |  |  | Module 3 | Maintenance and Service Charge
Table Screen | [5 empty] | Model Design
Add Credit | [5 empty] | Business logic
Add Debit | [5 empty] | Data import and export
Remove Record | [5 empty] | Database design (ERD)
Input Validation | [5 empty] | Database Syncronization
API Design & Development
Module 4 | Petty Cash |  |  |  |  | Module 4 | Petty Cash
Table Screen | [5 empty] | Model Design
Add Credit | [5 empty] | Business logic
Add Debit | [5 empty] | Data import and export
Input Validation | [5 empty] | Database design (ERD)
Remove Record | [5 empty] | Database Syncronization
Module 5 | Invoice |  |  |  |  | Module 5 | Invoice
Invoice Table | [5 empty] | Model Design
Create Invoice | [5 empty] | Business logic
Input Validation | [5 empty] | Consume Payment API
Dialy Invoice Table | [5 empty] | Model Design
Dialy Payment Table | [5 empty] | Business logic
API Design & Development
Module 6 | Power |  |  |  |  | Module 6 | Database Design
Power Usage Table | [5 empty] | Model Design
Create Generator | [5 empty] | Business logic
Delete Generator | [5 empty] | Analytics
On Generator | [5 empty] | API Design & Development
Off Generator | [5 empty] | Data import and export
On PHCN | [5 empty] | Database design (ERD)
Off PHCN | [5 empty] | Database Syncronization
Delete Power Usage
Update Power Usage | [5 empty] | Module 7 | Attendance
Model Design
Module 7 | Attendance |  |  |  |  | Business logic
User Screen | [5 empty] | Analytics
Attendance Table | [5 empty] | API Design & Development
Add Sign in | [5 empty] | Data import and export
Add Sign out | [5 empty] | Database design (ERD)
Database Syncronization