## Artisan Connect
[5 empty] | Project Start Date: | 2022-02-20
Frontend | [6 empty] | Backend
Milestone 1 | Authentication | [5 empty] | Milestone 1 | Authentication |  |  |  | LEGEND
Tasks | Timeline |  | Comment | Status |  |  | Tasks | Timeline |  | Comment | Satus |  | Pending
| Start Date | End Date | [5 empty] | Start Date | End Date |  |  |  | Completed
Login Form | [6 empty] | Boostrapping | [5 empty] | In-Progress
Signup Form | [6 empty] | Model Design/Creation | [5 empty] | Cancel
Forget Password Form | [6 empty] | Unit Testing |  |  | Integration test pending
Login Form Input Validation | [6 empty] | Input Validation (Fluent Validator)
Signup Form Input Validation | [6 empty] | JWT Auth
Reset Form Input Validation | [6 empty] | Access Token Generation
Login Form Responsive Design | [6 empty] | Refresh Token Generation
Signup Form Responsive Design | [6 empty] | Token Validation
Reset Form Responsive Design | [6 empty] | Token Encryption
Stay login | [6 empty] | Email Varification
Token storage | [6 empty] | Password Varification
API Integration | [6 empty] | API Design |  |  | Awaiting QA
API Development:
Milestone 2 | User Profile | [5 empty] | 1. Login API
2. Signup API
Code Refactor | [6 empty] | 3. Verify Email API
Responsive Design with Bootstrap 5 | [6 empty] | 4. Refresh Token API
Global Config | [6 empty] | 5. Validate Refresh Token API
1. Color Config | [6 empty] | 6. Revoke Token API
2. Font Family Config | [6 empty] | 7. Forget Password API
Design Forbidden Page | [6 empty] | 8. Logout API
Design Error 404 Page | [6 empty] | 9. Keep Me Login
Design Email Confirmation Page | [6 empty] | 9. Hosting |  |  | Hosting account cannot be accessed
Design User Profile Page
1. Edit Profile | [6 empty] | Milestone 2 | User Profile & Authorization
2. Change Password | [6 empty] | Caching System |  |  | Improve data fetch performance
3. Upload Profile Picture | [6 empty] | Role & Permission Management
4. Delete Account | [6 empty] | Authorization
Design Admin Page | [6 empty] | 1. Role-based Authorization
1. Can View All Users Profiles | [6 empty] | 2. Policy-based Authorization |  |  | Route guard secured resources
2. Can View All Artisans Accounts | [6 empty] | Authorization Middleware
3. Can Create Artisan | [6 empty] | App Search
4. Can Delete Artisan | [6 empty] | 1. Global search
5. Can Suspend Artisan | [6 empty] | 2. Content Specific Search
API Integration | [6 empty] | Email Server Configuration
Model Design/Creation
Unit Testing
Data Validation (Fluent Validator)
Account Suspension
Account Deletion
Document upload
[7 empty] | Milestone 3 | User Profile & Authorization
[7 empty] | Milestone 4 | Database Design
ER Definition
ER Design
Database Configuration
Model Configuration
Model Mapping
Schema Creation

## Facility Management
[5 empty] | Project Start | 2022-02-20
Frontend | [6 empty] | Backend
Milestone 1 | Authentication | [5 empty] | Milestone 1 | Authentication
| Project | Tasks | Timeline | Comment |  |  |  | Project | Tasks | Timeline | Comment
Milestone 2 | User Profile | [5 empty] | Milestone 2 | User Profile